JECRC Medical College, Hospital & Research Centre

Central Buying Unit - Note Sheet -01

Supply Chain Management - (Procurement & Stores)

Ref. No.: JECRC Hospital 01/2026-27 	                                               Date: 31st August 2026

Department: Supply Chain Management Department (Procurement & Stores)

Approval for Supply, Installation, Testing & Commissioning (SITC) of Liquid Medical Oxygen (LMO) Storage System

1. Background

In a Greenfield multi-specialty healthcare project; continuous availability of Medical Oxygen is a critical, statutory and essential operational requirement for patient care, particularly in Critical Care Units, Operation Theatres, Emergency, NICU, PICU and other oxygen-dependent clinical areas.

To establish a safe, reliable and uninterrupted Medical Oxygen supply system before commissioning the hospital, the Supply Chain Management Department initiated the procurement process for the Supply, Installation, Testing & Commissioning (SITC) of a Liquid Medical Oxygen (LMO) Storage System at the hospital premises.

2. Procurement Process

Budgetary and commercial proposals were invited from reputed dealers & manufacturers who have proven experience in installation and maintenance of Medical Oxygen Storage Systems for healthcare institutions.

The following Six (6) vendors participated in the procurement process: INOX Air Products, Linde India Ltd., Wilson (Dealer), Shakti Gases, Air Liquide, Vayu Products

3. Technical & Commercial Evaluation

All offers received were evaluated jointly based on technical suitability and commercial competitiveness. (in CBU Meeting -01)

The evaluation criteria included-Compliance with technical specifications, Experience in healthcare installations, Delivery schedule, Installation & commissioning capability, Warranty and after-sales support, Annual operating cost. Price competitiveness. Overall Life Cycle Cost (LCC)

4. Commercial Negotiations

To obtain the most competitive commercial terms, multiple rounds of negotiations were conducted with the participating vendors.

| Meeting | Date | Purpose |
| --- | --- | --- |
| CBU Meeting – 01 | 19 May 2026 | Initial commercial negotiation |
| Negotiation – II | 26 May 2026 | Revised commercial offer |
| Negotiation – III | 02 July 2026 | Final price negotiation & commercial closure |

Following completion of negotiations, the final commercial offers were compared and evaluated.

Also, we had discussed for Various types of Portable Cylinders and It is Suggested to compare with local vendor and finalized for supply of Medical Gases.

5. Final Commercial Offer – L1 Vendor

|  |  |  |  | Vendor 1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Vendor Name |  |  | Inox Air Products |  |  |  |  |
|  | Contact No. |  |  | Akash |  |  |  |  |
|  | Model No. |  |  | 9999596836 |  |  |  |  |
|  | Tank Capacity & Location |  |  | 13 KL + 06 KL (BHIWADI) |  |  |  |  |
| S no. | Particulars | UOM | Qty | Initial Quoted Price (INR) | Negotiated Price (INR) 19th May 2026 | 2nd (26 May 2026) | 3rd Meetings (2nd July 2026) | Total Amount (INR) |
| 1 | Basic Price for LMO (Monthly) | SM3 | 13000 | 11.80 | 10.25 | 10.25 | 10.25 | 133,250 |
| 2 | Delivery/Transportation Charges (Monthly) | SM3 | 13000 | 2.89 | 2.50 | 1.75 | 1.75 | 22,750 |
| 3 | Fixed Facility Charges for 13 KL | Monthly | 12 | 15,000 | 12,500 | 12,000 | 11,000 | 132,000 |
|  | Sub Total (INR) |  |  |  |  |  |  | 288,000 |
|  | GST - Item 1 & 2 - 5% & Item no. 3 - 18% |  |  |  |  |  |  |  |
| 4 | One time Asset Installation & Commissioning Charges | Nos | 1 | 150,000 | 135,000 |  | 135,000 | 135,000 |
| 5 | Storage Tank and Vaporizer Mobilization from our base to hospital. | One Time | 1 | Included |  |  | Included |  |
| 6 | PESO License work Fee (Govt.) for 5 years | One time | 13KL+ 06 KL | 200,000 | 200,000 | 200,000 | 200,000 | 200,000 |
| 7 | PESO License work Fee (Vendor) | One time | 1 | On Actual | On Actual | On Actual |  | On Actual |
| 8 | Automatic Alarm System (O & ED) | Nos | 1 | Included |  |  |  | - |
| 9 | Telemetry | Nos | 1 | Included |  |  |  | - |
|  | Sub Total (INR) |  |  |  |  |  |  | 335,000 |
|  | GST Extra | 18% |  |  |  |  |  | 60,300 |
|  | Grand Total (INR) |  |  |  |  |  |  | 395,300 |
|  | Payment Terms (for SITC) |  |  | 100% Advance |  |  |  |  |
|  | Payment Terms (for Medical Gases) |  |  | Within 30 days |  |  |  |  |
|  | Delivery Time & Completion |  |  | 8 Weeks to 10 Weeks |  |  |  |  |
|  | Minimum Agreement Tenure | Years |  | 10 Years |  |  |  |  |
|  | Agreement Lock in period | Years |  | 10 Years |  |  |  |  |
|  | Complete Civil work | - |  | Hospital Scope |  |  |  |  |
|  | Price Escalation |  |  | Fixed for 2 years, 5% Y on Y Or Formula Based, whichever is lesser |  |  |  |  |
|  | Mode of Delivery |  |  | Weighment Basis |  |  |  |  |
|  | Minimum Expected Volume | Monthly |  | will review after 2 years 6 months (NO MG) |  |  |  |  |

Inox will be responsible for procurement of all approvals from various government agencies and the charges for the same shall be paid by JMCHRC (A Unit of JU on Actuals).

All Charges will be borne by JMCHRC Hospital other than above mentioned, if it is required for obtaining license work.

7. Comparative Evaluation

A detailed Comparative Statement (CST) of all participating vendors has been prepared and attached with this Note Sheet; After detailed technical scrutiny and commercial evaluation:

- Technical Evaluation: Technically Responsive

- Commercial Evaluation: L-1 (Lowest Evaluated Bidder)

M/s INOX Air Products has emerged as the Lowest (L-1) responsive bidder and offers the most economical solution while fully complying with the technical requirements.

8. Recommendation

The Supply Chain Management Department recommends awarding the work of:

Supply, Installation, Testing & Commissioning (SITC) of the Liquid Medical Oxygen (LMO) Storage System

Proposed Payment System – LMO Storage System

- SITC Payment:

  - 100% advance payment shall be released against the approved Purchase Order/Letter of Intent/Agreement Copy for the SITC component, as per the negotiated commercial terms.

  - The advance shall be released only after completion of all necessary contractual and documentation formalities.

  - The vendor shall submit the required Advance Payment Invoice, Purchase Order/LOI, bank details, and applicable statutory documents before release of payment.

- Medical Gas Supply Payment:

  - Payment for actual consumption/supply of Medical Oxygen shall be made within 30 days from the date of submission and acceptance of the invoice.

  - Invoices shall be supported by applicable delivery documents, weighment records/consumption statements and other required supporting documents.

  - Payment shall be processed based on the actual quantity supplied/consumed as per the agreed commercial terms.

- Installation & Commissioning:

  - The SITC advance shall cover the agreed installation and commissioning scope as per the approved commercial offer.

  - The vendor shall complete installation, testing and commissioning within the agreed 8–10 weeks completion period.

  - Any applicable statutory deductions, taxes or statutory compliances shall be dealt with as per prevailing rules and the Purchase Order terms.

- Statutory & Licensing Payments:

  - PESO Government licence fees for the agreed scope shall be paid as per the approved commercial offer.

  - The Note Sheet specifies the PESO licence work fee for 5 years at ₹2,00,000 for the 13 KL + 06 KL system.

  - Any additional statutory charges required by government authorities, where specifically applicable, shall be processed on actuals as per the approved terms.

- Commercial Control:

  - No payment beyond the approved Purchase Order/LOI value shall be released without prior written approval of the competent authority.

  - Any variation in scope, quantity, price or statutory charges shall require prior approval before commitment.

  - All invoices shall be verified by the concerned Technical/Engineering, Supply Chain and Finance/Accounts teams before payment processing.

- Price & Contractual Terms:

  - Medical Gas pricing shall remain fixed for the initial 2 years, followed by an annual escalation of 5% Year-on-Year or formula-based escalation, whichever is lower, as per the negotiated commercial terms.

  - The minimum agreement tenure and lock-in period shall be 10 years, as approved.

  - The agreed payment mechanism shall form an integral part of the Purchase Order/Agreement.

- Recommended Payment Approval:

  - SITC Component: 100% Advance.

  - Medical Gas Supply: Payment within 30 days of accepted invoice.

  - Statutory/License Charges: As per approved commercial terms and on actuals, wherever applicable.

  - Any additional/variation payment: Only against prior written approval of the competent authority.

to

M/s INOX Air Products

at the negotiated commercial rates and terms mentioned above.

The recommendation is based on:

- Lowest evaluated commercial offer (L-1)

- Technical compliance

- Proven experience in healthcare LMO installations

- Competitive operating cost

- Favorable commercial terms

- Reliable service support and maintenance capability

9. Approval Requested

Approval is requested for:

- Award of SITC work to M/s INOX Air Products.

- Approval of the negotiated commercial rates and terms.

- Issuance of Purchase Order/Letter of Intent.

- Execution of a 10-year agreement as per the approved commercial terms.

- Release of the applicable advance payment for SITC activities as per the agreed payment terms.

Enclosures

- Commercial Comparison Sheet

- Vendor Final Commercial Offer

| Particulars | Designation | Employee Name | Signature |
| --- | --- | --- | --- |
| Written By | Executive – Supply Chain Management | Mr. Akash Kumar |  |
| Technical Inputs Vetted by | Sr. Medical Advisor | Dr Shrikant Swami |  |
| Commercials Reviewed By | General Manager – Supply Chain Management | Mr. Santosh Gupta |  |
| Recommended By | Chief Executive Officer-JMCHRC | Mr. Prateem Tamboli |  |
| Approved By | President – JECRC University | Prof Victor Gambhir |  |